## Internal Regression Testing
Portal | Group | Issue | Details | Priority | Status | Issue Date | Completion Date | Developer Comments
All | Fields | Property min bid default and min insurance | these two fields don't seem to serve any function. Maybe we should hide them for now. It seems like bad UX to have a field that doesn't do anything. | Low | Deferred |  |  | Review later.
All | Invoices | Zero win fee invoice | Vendor 2 has a zero invoice for a $2000 win | High | Ready for PROD
All | Notifications | Action bells | These do not appear to be consistent in their meanings | Medium | Complete |  |  | Need to evaluate action bells
All | Notifications | Action bells | When clicked by user, they don't take you to the item needing action | Medium | Ready for PROD |  |  | Need to evaluate action bells
Android | Fields | The bid due date and bid response date that are defaulted are invalid to proceed. | The bid due date and bid response date that are defaulted are invalid to proceed. The user should be able to accept the defaults and proceed. It is not helpful to have a default date that doesn't pass validations | High | Ready for PROD |  |  | Will Recheck after deploy to Local Environment, Possible timezone issues
Android | Fields | Bid date validation issues | The UI is not allowing the bid response and bid due dates to be the same. The default is "today" if I make the bid due date "tomorrow" then attempt the make the response date the same the error message is that the response date cannot be after the bid due date. It is not. They are the same. this condition is allowed in iOS | High | Ready for PROD |  |  | Will Recheck after deploy to Local Environment, Possible timezone issues
Android | Fields | Work Order bid response date rules | Work Order requires the response due date to be 5 days in the future but bid request does not have this rule. | Medium | Ready for PROD | 2020-11-01 |  | This is working as Company Default setting
Android | Layout | Look and feel | Vendor detail page needs more space at the bottom under the insurance amount and expiration date fields. Te page is cut off on the Android platform | High | Not Started | 2020-11-08
Android | Navigation | Work Order Navigation Issues | When entering in the details of a work order on Android the property and service type search does not work. Intellitype works, but would require the user to know the property name or service name. The spyglass implies that it is clickable to drop down or search for options. | High | Complete | 2020-11-01
Android | Notifications | Android is unstable and needs to be reinstalled each time there is a notification. | The app crashed when logged in to Manager_4 after vendor_2 accepted and then again when vendor_2 sent a note. After re-install the change was visible but no notifications were displayed. This works on iOS. Android crashes each time you go to the Home page when there is a notification. Android is unstable at this point due to unstable notifications. I cannot move forward when the app needs to be reinstalled during testing. | High | Failed PROD | 2020-11-15 |  | Failed in version 20
Android | Unsable | Navigation | When clicking across the icons in the bottom tray if the user navigates back and forth between screens too quickly the application will crash. | High | Failed PROD | 2020-11-15 |  | Failed in version 20
android | Localization | Expiration is called "Expiery" | In the US people are more used to the word Expiration date, not Expiery Date. | High | Not Started | 2020-11-08
Android | stability | "unfortunatly, AssociationBids has stopped." | This time the crash happend unexpectidly. Not directly related to any specific action. The app seemed to survive notifications of a submission and message. | High | Not Started | 2020-11-12
Android&iOS | Messaging | Notes to Vendor during bid request process | On the web the notes tab is specific to a vendor. On iOD and Android the notes are not vendor specific. I checked Vendor_2 and see that he message is not shown to the vendor when entered via notes tab on mobile. | High | Not Started |  |  | As designed (Let's look at this together, There is a messages tab at a level is shouldn't be)
IOS | Attachments | Vendor upload of pictures and doc | Vendor can't upload pictures or documents (E.S. I was able to upload a picture, I wonder why we have different experience?) (SW - just tried again and still can't. Maybe I don't know how to.) | High | Deferred | 2020-11-15 |  | Need to review documents & pictures.
iOS | Attachments | Bid Request (Vendor) | Vendor can't see any uploaded documents "11/15 Doc try web" Bid Request | High | Complete | 2020-11-15 |  | I think Attachments is generally a discussion topic.A picture is not a document.
iOS | Attachments | Vendor response | No ability to add a document on iOS or picture when responding to a bid request or workorder | High | Deferred |  |  | Once a bid/work order is submitted, it's "locked".
iOS | Last Worked Date | All vendors have a last worked date that is the same as the response due date of the bid request when adding a new bid request on the vendor add screen | Last worked date should be updated for a vendor when a bid request they have won is marked complete. The default is null | High | Ready for PROD | 2020-11-01 |  | Will Recheck after deploy to Local Environment, Possible timezone issues
iOS | Bid Request | Association Bids Failed | a manager gets and "Association Bids Failed" message when attempting to accept a bid (Manager 4 accepting vendor 2 submission) I suspect that this is because the subitted start date is in the past. However we should have a better message or allow the vendor to resubmit if the submittal due date is extended. I did extend the submission due date from 11/2 to 11/8. (Please see screen shots #4 | High | Complete
iOS | Bid Request | Association Bids Failed | Also failed to accept vendor 2 submission on manager 4 workorder. This makes me this it is not about the due date. (Please see screen shot #4) | High | Complete
iOS | Bid Request | Bid Response & Due Date | For Vendors, the Bid Response & Due dates should be calculated when Bid / Work Order is submitted NOT when Bid / Work Order is created. This applies to Web & Andriod as well. i.e. Create a Bid Request (Response & Due dates are populated correctly. Don't submit the Bid -> Leave Bid Request and come back another day -> Submit the Bid Request (Note that the Response & Due dates were not updated) | High | Not Started | 2020-11-16
iOS | Attachments | New Workorder or new Bid request. | There is no opportunity to add a document to a new bid request or workorder | High | Deferred | 2020-11-08 |  | Only photos are allowed for now. Need to review how to add documents.
iOS | Attachments | Bid Request (Manager) | Manager can't click on any uploaded documents to view document details.. AND submission disapears in review process. | Medium | Failed PROD | 2020-11-15 |  | Added a word document to bid submission in Web as vendor then reviewed submission in iOS and there was no word document attached or any indication that a document was submitted. after no taking any action I went back to the bid details page then back to the vendor tab and at that time the submitted bid was mission (Vendor_2 and Manager_4) the data is there now to review submission on Nov15th bid
iOS | Navigation | Bid Request (Vendor) | Bid request details already in edit mode (Unlike all other screens which goes to a detail page and then "Edit" option). Not clear on which field to edit. * Applied to all screens in edit mode. | Low | Deferred |  |  | Review later.
iOS | Bid Request | Bid submission review doc | I cannot review the word document that the vendor attached to the bid submission. | High | Ready for QA
iOS | Navigation | Loss of Progress | When Creating a bid or workorder if a user added details on page one, moved to vendor or attachment page then moves back to detail page the entered data is lost. | Medium | Complete |  |  | Could't replicate -We have checked this issue with multiple scenarios but couldn't replicate. Can you please provide us a video with steps those you perform? if next time you will get this issue. => 11/10/2020
iOS | Messages | Top Level messages on Manager Portal | On both the bid and the workorder detail page there is a message tab that is not specific to any one vendor. When a vendor recor is open on either, ther is also the ability to message to a specific vendor. I am not sure who the recipient is of the top level message tab | High | Not Started | 2020-11-08 |  | Change "Submit" button to say "Add"
iOS | Notifications | Notifications | Not working for manager or vendor | High | Complete
iOS | Navigation | Home screen | After login, take first to Home screen. | Low | Ready for QA
iOS | Navigation | Work Orders | If you are adding a Work Order and skip the vendor add and go to the detail page, The user cannot go back and add a vendor via the wizard and cannot submit. It is possible to edit the work order to add a vendor but the wizard navigation is not consistent. | Medium | Failed PROD | 2020-11-15 |  | This is working same as Web (ES, you are actually incorrect. in the web the user cannot click on "review work order" button until a vendor is selected, in iOS you can causing the issue logged) Please look at the workorder "No Vend Submit" for proof that iOS will allow the user to go to the review step of add workorder and the web will not.
iOS | Property | New property not showing in dropdown | Add a new property. Go to Work Order, the newly added property doesn't show up on dropdown list. | High | Complete
iOS | Property | Error adding vendors | After the above error message, click "Ok". Select a vendor manually -> vendor doesn't show up on added vendor list. Go back to add vendor manually -> Previously added vendor no longer appear on the list. | High | Complete
iOS | Notifications | Home screen | Review notification text on home screen and notifications in general. | Low | Not Started | 2020-11-08 |  | Can you please provide Sharad and Eddie a list of all error message and notification statements in text for editing?
iOS | Work Order | Error adding vendors | Create a new Work Order, select property -> get "Association Bids failed" error message. | High | Complete
IOS | Notifications | Notifications | Green Color used is hard to read on a mobile device, Please change to a darker green color that is easier to read and less fluorescent. (See Screen Shot #3 for Nov 8th) |  | Not Started | 2020-11-08
iOS | Usability | The wrong iOS keyboad is activated: When adding property, bid, etc. data entry forms | Typically when entering data in a form the full spacebar keyboard is activated. However in the add property form the keyboad with the smapp spacebar and the prominant '@' is active. This keyboard is typical for when a user is entering in an email address. Please always use the typical keyboard unles actually entering an email address. | high | Not Started | 2020-11-15
iOS | Vendor & Manager | Notifications | When logged in as a vendor or manager, bottom navigation buttons doesn't show correct item count. When you click on the "Bid Request" or "Work Order" icons then the counts get updated. Counts of these two items should be updated when Vendor first logs on to the app. | Medium | Not Started | 2020-11-16
iOS | Vendor | Home screen | Bid Request and Work Order notification is the same on the home screen. Change lime green color that is used for work order notification. | Low | Not Started | 2020-11-16
iOS | Vendor | Home screen | When clicking on Work Order notification, the work order detail page doesn't hide bottom navigation. This is hidden when you go to the detail page from the work order page. | Low | Not Started | 2020-11-16
iOS | Vendor | Work Order | After accepting work order, the count on the bottom navigation doesn't include the current work order that was just accepted. | Low | Not Started | 2020-11-16
iOS | Vendor | Work Order | When entering Bid Amount, clear out Amount field if "$0.00" so vendor can start entering amount rather than having to clear out the 0.00 | Low | Not Started | 2020-11-16
iOS | Vendor | Work Order | Can't click on property address to map property. Can't click on manager's phone number to call manager. Can't click on manager's email to email manager. | Low | Not Started | 2020-11-16
iOS | Manager | Work Order | Get "Association Bids failed" message when accepting work order submitted by Vendor. | High | Not Started | 2020-11-16
iOS | Vendor | Profile | Vendor profile shows services drop down in detail view. Dropdown should be removed in detail view. | Low | Not Started | 2020-11-16
iOS | Vendor/Manager | Log Out | When logging out, can we save the email address so the user doesn't have to enter their email address all over again? | Low | Not Started | 2020-11-16
Web | Fields | New Vendor Registration | When a vendor was marked as duplicate, that vendor should be allowed to register again. System errors out saying the email already exists. This vendor is not accessible in any way and manager is not able to invite this vendor again. | Low | Ready for PROD
Web | refund | Refund (Vendor) | When vendor is requesting refund, allow notes for all categories including "Other". Currently notes only appear when "Other" is selected. | Low | Ready for PROD
Web | refund | Refund (Vendor) | Vendor didn't get email confirmation when refund was submitted. Is email sent to anyone at Association Bids? e.g. support@... | Medium | Ready for PROD |  |  | Need Sharad to re-Test
Web | Reports | No report/still can't see what a full bid report looks like | What do 5 bids looks like? what is the deliverable? | Enhancement 1 | Deferred
Web | Stability | Add Vendor | For invited vendor SCDK, screen flashes with full vendor details, then moves to consolidated format. Needs to go directly to consolidated format | High | Ready for PROD
Web | refund | Refund (Administrator) | Administrator can't apply partial refund. Make text box editable. (Validate refund amount <= invoice amount) |  | Deferred |  |  | As designed. Only full refunds are implemented/allowed at this time.
Web | Stability | Add Vendor | On first try, the system just spun and did not go onto the next step | Medium | Complete |  |  | Could't replicate
Web | Stability | Add Vendor | When inviting a vendor, system hangs at the spinning logo. Has to do with specific company: Try "Breakaway" as the company and "spatel@breakawaymgmt.com" as the email. | High | Not Started | 2020-11-16
Web | Administration | Approve Vendor | How to access vendors that have been set as "Mark As Duplicate" status. | Medium | Not Started | 2020-11-16
Web | refund | Refund (Vendor) | Invoice doesn't show refund applied to the invoice. | High | Not Started |  |  | As designed. Only full refunds implemented at this time
web | Stability | After accepting a bid request the focus goes to a screen that does not make sense | The Success screen just has a new message screen that is not affiliated to the bid. | Medium | Failed PROD | 2020-11-15 |  | See feedback screen shots in Error word doc Nov 2nd 2020 Attempted retest but "Association Bids Failed" messages appeares in iOS when attempting to accept a submission (Manager_4 and Vendor_2) this is the Nov 15th submission with an attached word doc.(See Nov 15th Screen shot)
Web | Stability | When submitting vendor bid, after submit, the page refreshes but stays on same page. No landing, no revert to home page. Gives appearance that nothing has happened. | When submitting vendor bid, after submit, the page refreshes but stays on same page. No landing, no revert to home page. Gives appearance that nothing has happened. | Medium | Complete | 2020-11-02 |  | See feedback screen shots in Error word doc Nov 2nd 2020
Web | Usability | Title | Does not tell us much. Think of revising to Job ID or Association or Client/Service requested | Enhancement 1 | Deferred
Web | Usability | Vendor Selction | When adding a new bid request a user is allowed to proceed from the bid detail page without adding a property. This prevents the app from pre-selecting vendors giveing a "No vendors selected" error message. If the user then goes back and adds the property (they would have no idea they need to do this) then returns to the vendor selection page, the vendors will be pre-selcted, but the error message persists and shouldn't. The fix is the prevent going to the next page of the wizard until all required fields on that page are complete. | high | Not Started | 2020-11-15 |  | Nov 15th testing cycle
Web | Usability | Vendor Star | The converse says "mark as unstar" Should just be "Unstar" and maybe a star graphic? (E.S. The star graphic on iOS works well, do you mean like that?) | Low | Failed PROD | 2020-11-15 |  | The text is changed but the "star" tool tip says "delete" and there is a '>' icon with the word "Star" and That makes no sense. Please just change to an empty or filled star icon with no words to serve the same function similar to how it works on the vendor listing page.
Web | Bid Request | Assign Vendors | When a Bid Request is created and vendors assigned, if vendor's do NOT respond within specified timeframe, system should automatically invite other vendors in this category. Refer to the "Withdraw from Bid Request" section in the "Workflow" document. | High |  | 2020-11-16

## Error List
Portal | Issue | Details | Priority | Status | Issue Date | Completion Date | Developer Comments
General | Email templates |  | Medium | Ready for PROD
General | Reset Password | After submitting new password, please redirect user to login page. (Right now it is a blank logo page only) | low | Ready for PROD
General | Notifications |  | High | Defered |  |  | Will complete with Notification
General | Scheduled jobs / bid requests |  | High | Ready for PROD
General | Reports |  | Medium | Ready for PROD
General | User Profile Card (Top Right) | Picture does not display, Title seems to default to "Web Designer". Chat, Activity and To-Do tabs are still there but not functional | Medium | Ready for PROD
General | Search algorithm |  | High | Ready for PROD
General | Dashboard | Not all part show data consistently with eachother (Vendor Portal example cshasek@gmail.com) | Medium | Ready for PROD
General | Counts / Left navigation & tabs | e.g. Bid request & work order counts (manager & vendor), vendor sub navigation items (admin) | Medium | Defered |  |  | Will complete with Notification
General | Content formatting | Money format: $9,999,999.99 Date format: mm/dd/yyyy Phone format: (999) 999-9999 General Number format: 999,999,999 | Low | Ready for PROD
General | Page number format | Last page count is not appearing correctly. Need to apply correct stylesheet. | Low | Already working
General | Left menu items collapsing | Left menu items should remain expanded as long as submenu items are being viewed | Low | Ready for PROD
General | Page number display | Page numbers are displayed when search narrows down to 0 results | Medium | Already working
General | Buttons not showing consistently | Some "Search" buttons are small while "Edit" buttons are large | Low | Ready for PROD
General | Profile image | Image showing as broken link when none uploaded. Show as stretched image with one is uploaded. | Low | Ready for PROD
General | Left menu items collapsing |  |  | Already working
General | Delete confirmation | All delete buttons should have a confirmation prompt | Medium | Ready for PROD |  |  | e.g. Admin portal -> delete management company
General | Edit / detail transition | All edited content should go back to the detail page | Medium | Ready for PROD
General | Email | A number of emails are sent from the application without using the Email Template table. Also, they're hard coded to use "http://clientassociationbids.visitmydemo.xyz" url rather than getting this from the web.config. | High | Ready for PROD | 2020-08-13
General | Property & Vendor approval | Since Latitude & Longitude are required to successfully get bids, an error should be displayed at creation/registration if address is invalid or Lat/Long not set. | High | Ready for PROD | 2020-10-07
Vendor Registration | Insurance date validation | Check for valid dates and StartDate < EndDate, RenewalDate & EndDate is in the future. | Medium | Ready for PROD
Vendor Registration | User agreement | Not showing from database | High | Ready for PROD
Admin | Vendor approval | Username shows first name. Should be email address. Can hide this section. | Medium | Ready for PROD
Admin | Vendor approval | Insurance & credit card info not showing. | High | Ready for PROD
Admin | Vendor approval | Can't edit any information on the approval page | High | Ready for QA
Admin | Vendor approval | Show radius selection made by vendor | Medium | Ready for PROD
Admin | Property delete | Should show confirm prompt & error message on same details page | Medium | Ready for PROD
Admin | Property delete | Search for property, delete message doesn't go away | Medium | Ready for PROD
General | Manager & Vendor portals | Bid Request (X) and Work Order (X) where X = Number of "Open" items (i.e. Status of "In Progress" or "Submitted"). Both pages should show only "Open" items by default when clicked. Same applies to mobile. | High | Ready for PROD | 2020-10-07
Admin | Vendor invite file | Error uploading file even with valid data | High | Complete
Admin | Vendor invite file | Company dropdown shows vendor list | High | Ready for PROD
Admin | Pricing | Need to add a new column in for % Fee. Fee will be calculated by range and then by $ or % | High | Ready for PROD
Admin | Delete company user | When deleting a company user, spinning logo appears and does not go to another page. In the database, user record is deleted. Also, even when this company is selected then the spinning logo appears and not displaying company details. | High | Ready for PROD | 2020-08-13
Vendor | Account management | - W-9 not working (hide left navigation item) - Insurance page not working - Billing / credit card information missing - Membership / can't edit cc | High | Ready for PROD
Vendor | Vendor Registration | Need to see the registration invoice show up showing payment and $0 balance | High | Ready for PROD
Vendor | Refund | Need to allow vendor to request a refund on a specific invoice with a choice or reason and the request needs to show up on the Admin portal with the reason. | Medium | Ready for PROD
Vendor | Profile | - Services not showing / should be editable - Radius selection not showing / should be editable | High | Ready for QA
Vendor | Content | Footer and right navigation not correct | Low | Ready for PROD
Vendor | Invoice | Format of header and from and to address should be reviewed | Medium | Ready for PROD
Vendor | Invoice | Add "Payment Applied" row and a "Balance" row at the bottom of the invoice | Medium | Ready for PROD
Vendor | Dashboard | Shows $100000.00 for new vendors and bottom statistics are also invalid (please also use comma in number formatting) | high | Ready for PROD
Vendor | Dashboard | User saltrat00@gmail.com shows $150000 on first webpart yet this vendor has never been awarded anything. However, User cshasek@gmail.com has been awarded $150000 and it shows on one webpart, but not others | High | Ready for PROD
Vendor | Work Order | Can't add vendor to work order / added vendor doesn't appear | High | Ready for PROD | 2020-10-05
General | Portal header | Remove "Administration Portal, "Manager Portal", and "Vendor Portal" from top header. | Low | Ready for PROD | 2020-10-01
General | Error Logging | Has this been implemented???? | High | Ready for PROD
Vendor | Dashboard | Top 5 items needing attention should appear | Medium | Defered |  |  | Will complete with Notification
Vendor | Dashboard | When manager accepted vendor's, vendor did NOT get "Congratulations" message on the dashboard. | Medium | Defered |  |  | Will complete with Notification
Vendor | Bid request | After accepting bid invitation, vendor can't submit bid until entering amount and date. "Submit Bid" button is disabled. Mark the Bid Amount field as required. Estimated start date is NOT required. | High | Ready for PROD
Vendor | Bid request | Bid request detail page is getting refreshed multiple times and different buttons appear and hide. Need to change this behavior. | High | Ready for PROD
Vendor | Bid request | Bid request search not working by Status. If easier just have 3 options: Open, Closed, Show All | High | Ready for PROD
Vendor | Bid request | When reviewing bid request details, the company name is showing as the vendor's company and not the management company's name. Also, the contact information is for the management company's contact and not the property manager's contact. Use the [BidRequest].[ResourceKey] field. | High | Ready for PROD
Vendor | Bid request | When manager accepted vendor's, a win fee invoice for the vendor was NOT generated. | High | Ready for PROD |  |  | Invoices are generated by job scheduled to run daily.
Vendor | Bid Request | Need to review win fee invoice to show payment and $0 balance | High | Ready for PROD
Vendor | Work order | Can't see work order that has passed response date i.e. status is still "In Progress". Scheled job should change status to "Closed / No Response" | High | Ready for PROD
Vendor | Profile | Unable to upload picture | Medium | Deferred |  |  | I believe we don't need to do anything on this as this time
Manager | Starred vendor | When starring a vendor - confirmation message doesn't show on the page until after you go to another page. | Medium | Ready for PROD
Manager | Staff directory | When logged in as a manager, the staff directory detail page shows the "Edit" button briefly before it's hidden. This needs to be handled at the server side scripting level rather than on the front end i.e. UI | High | Ready for PROD
Manager | Company settings | When logged in as a manager, should not see the "Company Settings" sub navigation under "Account Management". - This only happens when you follow these steps: - Click on Staff directory - Click on Account Management - Notice how the Company Settings option appears here | High | Ready for PROD
Manager | Bid request | Bid request search not working by Status. If easier just have 3 options: Open, Closed, Show All | High | Ready for PROD
Manager | Bid request | Bid request list page should only show open items. i.e. status of In Progress or Submitted | Medium | Ready for PROD
Vendor | Bid awarded | When bid was awarded to Vendor, work order was created and assigned to vendor BUT win fee invoice was NOT generated. Refer to work order titled "Garden" | High | Ready for PROD | 2020-10-01 | 2020-10-02
Vendor | Bid submit | Vendor is not able to upload any bid documents | High | Ready for PROD | 2020-10-01
Vendor | Bid Request details | When reviewing older bid requests or bid requests that have been closed, a "Bid Response Due Date has expired" message appears on top of the page. | High | Defered | 2020-10-01 |  | Question, Need to discuss
Vendor | Bid Request details | When reviewing older bid requests or bid requests that have been closed, the "Closed" and "Request Date Extension" buttons should not appear. | High | Defered | 2020-10-01 |  | Question, Need to discuss
Vendor | Bid Request details | When reviewing older bid requests or bid requests that have been closed, vendor should not be allowed to message property manager. | High | Defered | 2020-10-01 |  | Question, Need to discuss
Vendor | Insurance | When adding insurance information, if "End Date" is in the past then page doesn't allow user to manually enter valid date. Date has to be selected from calendar in order for validation to work. Also, End Date >= Renewal Date > Start Date | High | Ready for PROD | 2020-10-01
Vendor | Insurance | After vendor enters insurance information, there is no way to edit this information | High | Ready for PROD | 2020-10-01
Vendor | Insurance | Insurance dates entered as 10/10/2020, 10/20/2020, and 10/25/2020 for Start, End, and Renewal dates. However, insurance details show these as 10/9/2020, 10/19/2020, and 10/25/2020 on Vendor portal. (May be a formatting issue???) On Manager portal, expiration date shows correctly as 10/20/2020. | High | Defered | 2020-10-01 |  | Time Zone issue
Manager | Bid request | When manually adding a vendor, that vendor can not be removed until we go to the detail page. This vendor should be removable on the same step. | Medium | Already working
Manager | Bid request | When vendor has submitted a message. Show the bell icon next to that vendor. Maybe show a "message" icon? | Medium | Defered |  |  | Will complete with Notification
Manager | Bid request | When accepting a bid from a vendor, prompt the manager that other vendors will be rejected and a "Work Order" will be created for this bid request. Take the manager to the detail page for the newly created work order | Medium | Ready for PROD
Manager | Bid request | Populate missing vendors for when vendors reject a bid request or when they don't respond. | High | Ready for PROD
Manager | Bid request / work order | - When reviewing the vendor information in a popup, hide bid $ & date when vendor has NOT submitted any bids. - Insted of "Added On" on the popup, show "Estimated Start Date" | Medium | Ready for PROD
Manager | Bid Request | on the vendor search page the columns are VENDOR NAME & COMPANY NAME, However the data in the "Vendor Name" column is the contact info. The contact is not necessarially the vendor name. I think we should call this column "Contact Person" Like it is on the vendor selection page (VENDOR NAME CONTACT PERSON) also please reflect the same order of columns on the search results page to match the bid request vendor selection page (VENDOR NAME CONTACT PERSON) | Medium | Ready for PROD |  |  | Match the vendor list page format (i.e. colum names & data)
Manager | Work order | "Starred" vendor search not working when adding vendors | High | Ready for PROD
Manager | Invite New Vendor | The message "Record has been inserted successfully." seems too technical. Maybe change to "Invitation Sent" | low | Ready for PROD
Manager | Work order documents missing | - Create a work order and add a document - Don't add vendors - Go to another section of the site - Go back to the work order (detail page will not have the uploaded document) | High | Ready for PROD
Manager | Work order | After work order is marked as completed and after filling out the vendor rating, work order status is NOT changed. Need to show a confirmation message on the page. Also, hide the "Complete Work Order" and "Close Work Order" buttons. | High | Ready for PROD |  |  | Issue in Firefox browser only
Manager | Bid Request | When creating a new bid request, the vendor list page refreshes to show selected vendors. Refresh only the vendor list (Not the whole page). | Medium | Ready for PROD | 2020-10-01
Manager | Bid Request | When creating a new bid request, the details page is initially displayed with empty data then it refreshes to show bid request details. Page should display details at once when page is loaded. Alternatively, hide endire page and show loading logo until content is ready to show. | Medium | Ready for PROD | 2020-10-01 | 2020-10-06
Vendor | Credit Card | After vendor enters credit card information, there's no way to edit this information. | High | Deferred | 2020-10-22
Vendor | Account Management / Insurance | Website isn't accepting valid End and Renewal dates in the future i.e. for next year. | High | Ready for PROD | 2020-10-22
Vendor | Account Management / Insurance | After date is entered, when you go back to insurance dates saved, the dates are showing a day off. Check this for all areas on the site. | High | Ready for PROD | 2020-10-22
Vendor | Registration | Website isn't accepting valid End and Renewal dates in the future i.e. for next year. | High | Ready for PROD | 2020-10-22
Vendor | Registration | Manager invited vendor by entering company information. Vendor received email and clicked on link to go to the website. No company information entered by the manager was saved. Vendor couldn't enter same company name. Error message "Company Name" already exists! | High | Ready for PROD | 2020-10-22
Vendor | Top Action Items | Vendor is seeing top action items not related to current vendor. See attached photo in the "Error Document". Also, change section title to match that of the left. | High | Already working | 2020-10-22 |  | To verify
Vendor | Bid submit | Vendor submits a bid -> Is prompted to submit bid -> Vendor selects "Yes". It appears as thought the bid was submitted but none of the information entered was saved. | High | Ready for PROD | 2020-10-22
Vendor | Top Action Items | When clicking on action item (for Work order) opens a blank page. | High | Ready for PROD | 2020-10-22
Manager | Work Order | Adding vendor by "Last Worked Before" doesn't narrow down vendors | High | Ready for PROD | 2020-10-22
Manager | Dashboard | Work Order count is not correct. See attached photo on the "Error Document". | High | Ready for PROD | 2020-10-22
Admin | Dashboard | Dashboard has NaN displaying on page. | Low | Ready for PROD | 2020-10-22
Admin | Pricing | Can't enter a win fee of $125. System changes it back to $100. | High | Ready for PROD | 2020-10-22
Manager | Bid Request | On the bid request detail page, change the color for the bid request status as follows: In Progress (blue) Interested (yellow) Not Interested (red) Submitted / Accepted (green) The same color scheme should be applied to the Bid Request and Work Order list pages. | Low | Ready for PROD | 2020-10-01
Manager | Bid Request | On the bid request detail page, when reviewing bid request submitted by vendor, the insurance documents is not listed for review | High | Ready for PROD | 2020-10-01
Manager | Left Navigation / Bid Request | Bid Request left navigation menu should should show the number of "Open" bid requests count e.g. "Bid Request (2)" This is working correctly for Vendors | High | Defered | 2020-10-01
Manager | Left Navigation / Work Order | Work Order left navigation menu should should show the number of "Open" work orders count e.g. "Work Orders (2)" This is working correctly for Vendors | High | Defered | 2020-10-01
Manager | iOS | Bid Submitted but vis vendor Web bottom menu bar notification did not appear when already in the iOS app | High | Ready for PROD | 2020-10-03
Manager | web | Choose vendor pop up frozen. Must filter on stared vendors first, search, then filter on non-stared vendors, search and now vertical scroll will be frozen | high | Ready for PROD | 2020-10-03
manager | iOS | When accemtping bid and choosing Yes on pop up causes an "association Bids" fail error | high | Ready for PROD | 2020-10-03
Manager | iOS | when left side menu expanded, you can still click on portion of hidden right side. When touching the right side the left side menu shoud disapear. | high | Ready for PROD | 2020-10-03
Manager | iOS | Home page is just a list of chat and should be more of a dashboard like recent notifications that are actionable | high | Ready for PROD | 2020-10-03
manager | iOS | Propert and Vendor tab are not yet developed | high | Ready for PROD | 2020-10-03
manager | iOS | bottom menu notification counts are no longer appearing | high | Ready for PROD | 2020-10-03
manager | web | Invite vendor only the name and email address should be required fields, no other fields are required for vendor invitations | high | Ready for PROD | 2020-10-03 | 2020-10-07
manager | web | When a property required insurance ammount exceeds that of all qualified vendors the error says "vendor does not exist" can we make the message more meaningful like "Insurace requirements exceed all available vendors"? | Medium | Defered | 2020-10-03
manager | web | when adding a vendor to a bid request, the filter is not functioning.the name filter or any of the other criteria do not limit the vendor list. UPDATE: I did notice that the name filter does work when other filters have not been used previously. I also think there is a need to "Clear" filters on the pop up without closing the vendor search dialogue. | high | Ready for PROD | 2020-10-03
manager | web | when adding a vendor to a bid request the vendor pop up runs off the screen. the pop up should be appropriately sized to the browser screen and the vendor list itself should scroll with the search criteria staying visible to the user. | high | Ready for PROD | 2020-10-03
vendor | web | when adding insurance information the renewal date field validation logic has a lot of issues. Does not allow dates in the future and says renewal date must be after start date (it was) and after I type in a date of June 21, 2021 the data is populated with today's date, not the date I typed in. After that I am able to select dates within this week but after about 5 days in the futre I get back to the validation issues notes. Testing with Vendor 25 data. | high | Ready for PROD | 2020-10-03
manager | web | I have a new bid request in progress "correction on 3:59" for Property 3 under Manager 3 and cannot figure out why I cannot add a vendor. I made the default insurance amount for property 3 to be $400 and I made the Vendor 25 insurance amount $40,000 however when I select vendor 25 to add to the bid it gives an error with no explanation. If I was this property manager I would have no idea why I cannot add a vendor so this error processing fails the intuitive test. Need better messages. | high | Defered | 2020-10-03
Vendor Registration | web | validated payment method is required for registration | high | Already working | 2020-10-03
vendor | web | no invoice generated for Vendor 47 wind of Eddie's lawn bid. no win fee calculated or charged | high | Ready for PROD | 2020-10-03
manager | web | with property 1 set to $0 min insurance I started a bd and vendors were selected, canceled that bid, changed the property min insurance to $400 and started a bid where no vendors wer available. However I know that Vendor 47 has insurance of $40,000. UPDATE: after adding vendor 47 insurance again at a level of $40,000 and trying to add Vendor 47 to the $400 insurance limit bid request on property 1 I am still not able to add this vendor or any vendor. I don't think the insurance details are being handled correctly in the DB. | High | Defered | 2020-10-03
manager | iOS | Please replace the generic desktop icon with the small AB logo. | Medium | Ready for PROD | 2020-10-03
super admin | web | The primary contact field of the manager named as the company primary contact has a value of False. This is not intuitive. Maybe that field is redundant being displayed in that primary contact area. | Medium | Ready for PROD | 2020-10-03
Super Admin | Web | In all phone fields please format the 10 phone digites stored with the following format masking (999) 999-9999 | High | Ready for PROD | 2020-10-03
Super Admin | web | Vendor import has incorrect validation. Only company name and email are required fields. All other fields are optional on vendor inviration (Error message: Failed to Invite. Line 2 - CompanyName is Blank, Address1 is Blank, City is Blank, State is Blank, Zip is Blank..) | High | Ready for PROD | 2020-10-03
manager | web | As manager 1 I marked vendor 47 as "Star" and tried the add vendor filter for starred vendors as part of the bid request and the list was filterd to nothing. Vendor 47 should have continued to appear in the list. | high | Ready for PROD | 2020-10-03
manager | web | There is awork order in progress from a time when Property 1 had no minimum insurance requirements. Not that Property 1 has a $400 minimum insurance requirement the vendor for the "Eddie's Lawn" workorder is missing. We should not remove a vendor from an in progress workorder due to insurance requirements. We might want to falg it in some way, but that work has already been approved and started under previous conditions. We should talk more about how in-progress items are treated when insurance minimums change. | High | Defered | 2020-10-03
manager | web | The image attached to the "Eddie's Lawn" workorder is not longer viewable by the web user. I think this image was uploaded on iOS. Image title is "Hejsan" | High | Ready for PROD | 2020-10-03
Manager | Notification for "Not Interested" vendor status | Similar to email notifications, include notifications when vendor is "Not Interested" only if vendor is manually added. If vendor was added by the system then ignore the "Not Interested" notifications to the manager. | High | Ready for PROD | 2020-10-07
Manager | Accept bid | When manager accepts a bid, set the other vendors to "Rejected" only if that vendor submitted a bid i.e. status of "Submitted". If vendors were "Not Interested" or didn't submit a bid, then leave their status unchanged. How will this work for the vendor i.e. when manager has already accepted a bid but vendor has not submitted one (all within allocated time frame)?? | High | Deferred | 2020-10-07

## Portal Testing
Dev | ID | Portal | Modules | Pages | Priority | Status | Issue | Issue Date | Completion Date | Developer Comments
VR |  | Administrator Portal | Account Management |  | Medium | Ready for PROD | Sub navigation items should remain expanded when sub navigation menu items are being reviewed. | 2020-06-15 | 2020-07-03
VR | 69 | Administrator Portal | Agreements |  | Low | Ready for PROD | Remove "Description" column from list page | 2020-06-15 | 2020-06-18
VR | 69 | Administrator Portal | Agreements |  | Low | Ready for PROD | Agreement status shows green i.e. active but on detail page shows "Inactive" | 2020-06-15 | 2020-06-18
VR | 69 | Administrator Portal | Agreements |  | Low | Ready for PROD | Edit agreement page should show text box for description | 2020-06-15 | 2020-06-18
VR | 69 | Administrator Portal | Agreements |  | Medium | Ready for PROD | After updating an item go back to the detail page for that item rather than going to the list page. This applies to all sections of the website. | 2020-06-15 | 2020-06-18
VR | 69 | Administrator Portal | Agreements |  | Low | Ready for PROD | On the edit page, move "Delete" button next to "Update" button. This applies to all pages. | 2020-06-15 | 2020-06-18 | Not completed on All pages
JS | 31 | Administrator Portal | Company Management | Add Company | low | Ready for PROD | Switch "Legal Name" to 2nd column and make "Name" 1st column | 2020-06-15 | 2020-06-18 | Some errors on Company Management Pages
JS | 31 | Administrator Portal | Company Management | Add Company | Medium | Ready for PROD | Address is not required so "State" should not be required | 2020-06-15
JS | 31 | Administrator Portal | Company Management | Add Company | High | Ready for PROD | Company not added when adding new company with contact details. Adding a company without contact details works! | 2020-06-18 | 2020-07-03
| 31 | Administrator Portal | Company Management | Add Company | Medium | Ready for PROD | When adding management company, default "Days to Respond to Bid Requests" to 2 business days and "Due to Submit Days" to 10 business days. | 2020-06-25 | 2020-07-03
JS | 57 | Administrator Portal | Company Management | Add Company Primary Contact | Low | Ready for PROD | When adding a new management company, on the "Primary Contact" step, make this contact the primary contact i.e. select the checkbox by default. NOTE: At least one primary contact is required for each company. | 2020-06-15
JS | 32 | Administrator Portal | Company Management | Add Company Primary Contact | Medium | Ready for PROD | Make Contact Name required for primary contact and show First Name and Last Name fields rather than one "Contact Person Name" | 2020-06-15 | 2020-07-03
JS | 32 | Administrator Portal | Company Management | Add Company Primary Contact | High | Ready for PROD | When primary contact is added, add this primary contact to the "Administrator" group. | 2020-06-15 | 2020-07-03
JS | 32 | Administrator Portal | Company Management | Add Company Primary Contact | High | Ready for PROD | When primary contact is added, a user should be created for that contact (using email as the username) and an email to reset their password should be sent. | 2020-06-15 | 2020-07-03
JS | 46 | Administrator Portal | Company Management | Add Company Property | High | Ready for PROD | For the "Access" step, only show contacts that are from the selected company for which the property is being added. | 2020-06-15 | 2020-07-13
JS | 57 | Administrator Portal | Company Management | Add Company Users | High | Ready for PROD | Remove "User Role". Access should be determined based on Groups that this user belongs to. | 2020-06-15 | 2020-07-03
JS | 57 | Administrator Portal | Company Management | Add Company Users | Medium | Ready for PROD | Address is not required so "State" should not be required | 2020-06-15 | 2020-07-03
JS | 57 | Administrator Portal | Company Management | Add Company Users | High | Ready for PROD | On the "Groups" step no groups are listed. Should display Property Manager and Company Administrator groups. Can't move past this step since at least one group is required. | 2020-06-15
JS | 57 | Administrator Portal | Company Management | Add Company Users | Medium | Ready for PROD | Breadcrumb says Staff Directory instead of Company User and when clicked page doesn't load. | 2020-06-15 | 2020-07-15
| 32 | Administrator Portal | Company Management | Add Company Users | Medium | Not Started | When adding contacts, a username should default to their email address (not editable). No need for "Password" & "Confirm Password" text boxes. "Create Account" button will randomly generate password and email user a reset password link. | 2020-07-02
| 32 | Administrator Portal | Company Management | Add Company Users | Low | Not Started | After contact is added, there's no visual confirmation that contact was added successfully. | 2020-07-02
| 57 | Administrator Portal | Company Management | Add Company Users | High | Not Started | Couldn't add user with email address "admin-1-2@associationbids.com". Get an error message saying enter valid email address. | 2020-07-02 |  | We can not add email with some special characters including dash (-), Gmail is also not allowing on registration. - Need your input
JS | 41 | Administrator Portal | Company Management | Company Property | Low | Not Started | Do not show table header if no records are available. | 2020-06-15
JS | 38 | Administrator Portal | Company Management | Edit Company | Medium | Ready for PROD | When any piece of company information is updated then go back to the detail page and not the list page. This should be applied across the whole site. | 2020-06-15 | 2020-07-15
| 38 | Administrator Portal | Company Management | Edit Company | Medium | Not Started | Deleting a company (or any other item) should show modal window to confirm delete. | 2020-07-02
| 38 | Administrator Portal | Company Management | Edit Company | High | Not Started | When deleting a company record, get blank screen with spinning logo. | 2020-07-02
JS | 39 | Administrator Portal | Company Management | Edit Primary Contact | Medium | Not Started | When editing primary contact, include first and last name rather than one field for "Contact Person Name" | 2020-06-18
JS | 39 | Administrator Portal | Company Management | Edit Primary Contact | Low | Ready for PROD | Bread crumb should say "Management Companies / Management Company / Primary Contact" | 2020-06-15
JS | 30 | Administrator Portal | Company Management | Listing Page | Medium | Ready for PROD | Company name not showing on list page (I believe Legal Name is referenced on this page instead of company name) | 2020-06-15
JS | 30 | Administrator Portal | Company Management | Listing Page | Medium | Ready for PROD | Company primary contact name not showing on list page (I didn't add a contact name when i first created the company but then updated the contact name and it still didn't show up on the list page.) | 2020-06-15
JS | 37 | Administrator Portal | Company Management | View Company | Low | Not Started | Property and User tabs should have a count of records along side tab | 2020-06-15
| 37 | Administrator Portal | Company Management | View Company | Medium | Not Started | Tabs should show count of "Property" and "User" items next to the tab. This applies to all tabs. | 2020-07-02
| 26 | Administrator Portal | Email Templates |  |  | Not Started | Email template type not finalized yet so leave as "In Progress" as opposed to in a "Complete" state. | 2020-06-15
| 34 | Administrator Portal | Notification Templates |  |  | Not Started | Notification type not finalized yet so leave as "In Progress" as opposed to in a "Complete" state. | 2020-06-15
| 34 | Administrator Portal | Notification Templates |  | High | Ready for PROD | Clicking on view icon throws an error | 2020-06-15 | 2020-07-03
VP | 77 | Administrator Portal | Pricing |  | High | Ready for PROD | Pricing applies only to the "Association Bids" company. There's no specific pricing for each of the management companies. Remove "Company" drop down from all pages. | 2020-06-15 | 2020-06-18
VP | 77 | Administrator Portal | Pricing |  | High | Ready for PROD | The edit pricing has a "Clear" button. Please replace that with a "Cancel" button to go back to the detail page. | 2020-06-15 | 2020-06-18
| 23 | Administrator Portal | Staff Directory | Add Page Steps | Medium | Not Started | When adding Staff user account use email address as username and assign default password. No need to ask for username and password on this step. | 2020-06-15
| 23 | Administrator Portal | Staff Directory | Add Page Steps | High | Ready for PROD | Blank page when adding staff member. Couldn't add staff member. | 2020-06-15 | 2020-07-03
| 23 | Administrator Portal | Staff Directory | Add Page Steps | Medium | Not Started | Use the staff's email address as username and random password to generate user account. Show email and "Create Account" button. | 2020-06-18
| 25 | Administrator Portal | Staff Directory | Edit Pages | Medium | Not Started | Username should not be editable. This should be the same as their email address. | 2020-06-18
| 25 | Administrator Portal | Staff Directory | Edit Pages | Medium | Not Started | When contact's email address is updated, make sure to update username to the new email address and send an email to the updated email to inform them that they should use this new email address to log in. | 2020-06-18
| 22 | Administrator Portal | Staff Directory | Listing Page | Medium | Not Started | Advanced search not working | 2020-06-18
RR | 90 | Administrator Portal | Vendors | Invite Vendors | Medium | Ready for PROD | Can't edit invited vendor information in case contact information was added incorrectly or need to send another email reminder. | 2020-06-15 | 2020-06-18
RR | 90 | Administrator Portal | Vendors | Invite Vendors | Low | Ready for PROD | Remove "Services" and "Insurance" section on view page. | 2020-06-15 | 2020-06-18
| 90 | Administrator Portal | Vendors | Invite Vendors | Low | Not Started | Show date added in the db as "Invited Date" on front end to show when vendor was invited. | 2020-06-22
| 90 | Administrator Portal | Vendors | Invite Vendors | Low | Not Started | Rename "Edit and Invite again" button to say "Edit". Add a "Resend Invitation" button to resend invitation. Currently you can only do so by editing the information. | 2020-06-22
| 90 | Administrator Portal | Vendors | Invite Vendors | Low | Not Started | On the edit page rename "Resend Invitation" to "Save & Resend Invitation" | 2020-06-22
| 42 | Administrator Portal | Vendors | Listing | High | Ready for PROD | Can see 11 vendors on manager portal but only see 1 vendor on admin portal. All vendors that appear on the manager portal should also be viewable on the admin portal. | 2020-06-25 | 2020-07-03
RR | 93 | Administrator Portal | Vendors | Upload Vendors | Low | Not Started | Add a "Vendor Import File" button to download the Excel file with field names of information to upload vendor. | 2020-06-15
RR | 93 | Administrator Portal | Vendors | Upload Vendors | High | Ready for PROD | The "Upload Vendor" button should open a modal window with a management company dropdown and a file upload option. | 2020-06-15 | 2020-07-03
| 93 | Administrator Portal | Vendors | Upload Vendors | Medium | Not Started | Not all management companies are displayed in the company dropdown on the vendor upload modal. | 2020-06-22
| 93 | Administrator Portal | Vendors | Upload Vendors | High | Ready for PROD | After uploading downloaded excel file, error message says please choose valid .csv file type. | 2020-06-22 | 2020-07-03
SP | 21 | Property Manager | Bid Requests | Add Bid Request Step 1 | High | Ready for PROD | Vendors don't have any services selected so bid request not listing this vendors. Moreover can't search of any vendors either. | 2020-06-11 | 2020-06-18
SP | 21 | Property Manager | Bid Requests | Add Bid Request Step 1 | High | Ready for PROD | Property list shows all properties even those that current manager doesn't have access to. | 2020-06-15 | 2020-07-03
| 21 | Property Manager | Bid Requests | Add Bid Request Step 1 | Medium | Not Started | Set default values of Response Due Date and Bid Due Date based on management company default values. | 2020-06-25
| 21 | Property Manager | Bid Requests | Add Bid Request Step 1 | High | Ready for PROD | When logged in as company admin, admin can see properties from other management companies (login as admin1@associationbids.com and see Property 3 - 1, Property 3 - 2 | 2020-07-02 | 2020-07-04
| 21 | Property Manager | Bid Requests | Add Bid Request Step 1 | Medium | Not Started | When on the the property detail/view page. Click on "Add Bid Request" then this property should already be selected on this step. | 2020-07-16 | 2020-07-04
| 21 | Property Manager | Bid Requests | Add Bid Request Step 1 | Medium | Not Started | Default "Response due date" to 2 business days from today, "Bid due date" to 10 business days from today | 2020-07-16 | 2020-07-04
| 27 | Property Manager | Bid Requests | Add Bid Request Step 2 | Medium | Not Started | Allow multiple document upload. This also applies on the detail/view page. | 2020-06-18
SP | 21 | Property Manager | Bid Requests | Add Bid Request Step 3 | Low | Not Started | When listing added vendors, vendor list is not displayed correctly. | 2020-06-15
SP | 21 | Property Manager | Bid Requests | Add Bid Request Step 3 | Low | Not Started | Change "Next" button to "Review Bid Request" | 2020-06-15
SP | 21 | Property Manager | Bid Requests | Add Bid Request Step 3 | High | Ready for PROD | When vendors are added, "Vendor Company" was added but this vendor doesn't show up on the Vendor list page | 2020-06-15 | 2020-07-03
SP | 21 | Property Manager | Bid Requests | Add Bid Request Step 3 | Low | Not Started | If no vendors exist then display a message showing no vendors exist. | 2020-06-15
| 21 | Property Manager | Bid Requests | Add Bid Request Step 3 | Low | Not Started | The "Review Bid" link should say "Review Vendor" if a bid has not been submitted by the vendor. Hide the bid $ details also if no bid is available. | 2020-06-18
| 21 | Property Manager | Bid Requests | Add Bid Request Step 3 | High | Ready for PROD | After manually adding vendors using the "+ Add Vendor" button, manager can NOT remove this vendor. This should be allowed only for vendors that are manually added by the manager and not those that are added automatically by the system. | 2020-07-02 | 2020-07-15
| 35 | Property Manager | Bid Requests | Add Bid Request Step 3 - Vendor Search Pop up | High | Ready for PROD | After selecting the "+ Add Vendor" button, pop-up show additional vendors. Clicking "Add" on the vendor popup does NOT add the vendor to the bid request vendor pool. Same issue happens when adding additional vendors from the detail page. | 2020-06-18 | 2020-07-03
SP |  | Property Manager | Bid Requests | bid listing | Medium |  | Need Property name as a column available on the bid list knowing that some managers may manage more than one property. | 2020-06-19
| 45 | Property Manager | Bid Requests | Edit Bid request | Low | Not Started | Delete popup currently is a javascript button. Replace with modal popup. | 2020-06-11
| 45 | Property Manager | Bid Requests | Edit Bid request | High | Ready for PROD | Property and Service should NOT be editable | 2020-06-18 | 2020-07-03
| 45 | Property Manager | Bid Requests | Edit Bid request | High | Ready for PROD | Allow manager to extend dates for each vendor to respond or submit bid and/or work orders | 2020-07-02 | 2020-07-13
| 60 | Property Manager | Bid Requests | Edit bid request - Notes | Low | Not Started | Notes don't have a title so change current design to use a card instead with notes and date. | 2020-06-18
| 60 | Property Manager | Bid Requests | Edit bid request - Notes | Low | Not Started | Show counter next to "Notes" tab. This applies to all tabs with a list. | 2020-06-18
| 20 | Property Manager | Bid Requests | Listing Page | Low | Not Started | Date should be in MM/dd/yyyy format (applies to all pages) | 2020-06-11
| 20 | Property Manager | Bid Requests | Listing Page | Medium | Not Started | "Carpet Cleaning One" bid request shows 5 bids when only 1 was submitted by the vendor. | 2020-06-18
SP |  | Property Manager | Bid Requests | New Bid Request | Medium | Complete | The prepopulated vendor list in the wizard included a Carpentry vendor when the requested service was Air Conditioning (Bella Capri, Clean Coils) | 2020-06-19 | 2020-06-22
|  | Property Manager | Bid Requests | View Bid request | High | Ready for PROD | Should have "Submit Bid" button to submit bid to vendors | 2020-06-11 | 2020-06-18
| 44 | Property Manager | Bid Requests | View Bid request | High | Ready for PROD | Breadcrumb for "Bid Request Detail" throws an error. Refer to Image 1 of "Error Document" document. Couldn't add staff member. | 2020-06-11 | 2020-06-18
| 44 | Property Manager | Bid Requests | View Bid request | Medium | Not Started | Once bid request is submitted. Display confirmation alert that bid has been submitted successfully. Update the vendor bid status as well on the page. | 2020-06-18
| 44 | Property Manager | Bid Requests | View Bid request | Low | Not Started | "Submit" button appears in the bread crumb area | 2020-06-15
| 44 | Property Manager | Bid Requests | View Bid request | Medium | Not Started | In the vendor section on this page, show the company name instead of the primary contact name. | 2020-06-15
| 44 | Property Manager | Bid Requests | View Bid request | Low | Not Started | In the vendor section on this page don't show the "Review Bid" or disable it if no bids have been submitted by the vendor | 2020-06-15
|  | Property Manager | Bid Requests | Add additional X vendors to bid request | High | Not Started | When a vendor declines the bid invitation or doesn't respond within the time allocated then system should automatically add X number of vendors to the bid request and send out invitations. This should be done until we get a response from the vendor or no more vendors exist for this service category.
| 5 | Property Manager | Profile | Edit Profile | Medium | Ready for PROD | Profile page should go to view page (not edit page) and then when edited should go to the edit page. | 2020-06-11 | 2020-06-18
PG | 7 | Property Manager | Properties | Add Property | Medium | Ready for PROD | When adding a property, automatically add current property manager to the property in step 3. Additional managers can be assigned to the property as well but current manager should automatically be given access. | 2020-06-11 | 2020-06-18
PG | 7 | Property Manager | Properties | Add Property | High | Ready for PROD | When assigning managers to a property, only list managers part of current company and that are part of the "Manager" group. | 2020-06-15 | 2020-06-18
PG | 7 | Property Manager | Properties | Add Property | Low | Ready for PROD | When adding documents and photos, photos should appear in a separate list with thumbnails. | 2020-06-15 | 2020-06-18
PG | 7 | Property Manager | Properties | Add Property | Low | Not Started | Change order of steps to Property -> Access -> Documents | 2020-06-15
| 7 | Property Manager | Properties | Add Property | High | Ready for PROD | Added a property and current manager was added to the property but when viewed on the detail page this manager didn't appear on the list of people who have access to this property. | 2020-06-22 | 2020-07-03
| 7 | Property Manager | Properties | Add Property | High | Ready for PROD | Adding property shows successful message but doesn't appear on manager's list. | 2020-07-02 | 2020-07-15
RR |  | Property Manager | Properties | Edit Properties | Medium |  | Unable to delete first manager even after a 2nd manager is added to the property in the same session. agree if only one manager they should not be able to be deleted, but if double click on the trash the page refreshes for no reason. | 2020-06-19
RR |  | Property Manager | Properties | Edit Properties | Medium |  | After creating a property with two manager (Bella Capri) I am not able to delete either manager to get it down to one manager | 2020-06-19
PG | 6 | Property Manager | Properties | Listing Page | High | Ready for PROD | List page should only display properties that manager has access to and more importantly only properties that are for his/her management company. | 2020-06-15 | 2020-06-18
PG | 6 | Property Manager | Properties | Listing Page | Medium | Ready for PROD | Advanced search not working | 2020-06-15 | 2020-06-18
| 10 | Property Manager | Properties | View Property | High | Ready for PROD | After adding a property, and having the current property manager selected to have access, this manager didn't show up on the view page of the new property. | 2020-06-18 | 2020-07-06
| 10 | Property Manager | Properties | View Property | Medium | Not Started | Uploaded documents can not be viewed. Show link on uploaded document to open in a new window. | 2020-06-25
|  | Property Manager | Property | View Property | Medium | Not Started | Cannot view attached file | 2020-06-15
| 2 | Property Manager | Staff Directory | Add Page Steps | High | Ready for PROD | Error when adding staff member (as property manager). Refer to Image 1 of "Error Document" document. Couldn't add staff member. | 2020-06-11 | 2020-06-18
| 2 | Property Manager | Staff Directory | Add Page Steps | High | Ready for PROD | Email should be unique for that company. No duplicate emails should be allowed when adding staff members. Emails will also be used as the username. | 2020-06-15 | 2020-06-18
| 2 | Property Manager | Staff Directory | Add Page Steps | Medium | Ready for PROD | On the "Groups" step, groups should be listed with a checkbox since staff member could be part of both groups. | 2020-06-15 | 2020-06-18
| 2 | Property Manager | Staff Directory | Add Page Steps | Medium | Not Started | When adding Staff user account use email address as username (make username read-only) and assign default password. No need to ask for username and password on this step. | 2020-06-15
| 1 | Property Manager | Staff Directory | Listing Page | Medium | Ready for PROD | Property Manager account that was used to log on to the site doesn't appear on this page. | 2020-06-11 | 2020-06-18
| 1 | Property Manager | Staff Directory | Listing Page | High | Ready for PROD | Property manager account that was used to log on to the site appears as Unapproved. However, this account was able to log on to the website. | 2020-06-15 | 2020-06-18
RR |  | property manager | Staff Directory | staff list | High | Complete | after failed attempt to add a staff member, the staff list is now blank. Previously there were many staff listed. When attempting to create a new staff both the property manager and administrator checkboxes were checked. (after sitting on the page for a time eventually a runtime error surfaced) | 2020-06-19 | 2020-06-22
| 3 | Property Manager | Staff Directory | View Pages | Medium | Not Started | When logged in as property manager, do not show the "Groups" and "User Account" sections on the page | 2020-06-25
PG | 18 | Property Manager | Vendors | Edit Vendor Details | Low | Complete | Should be able to edit & delete vendor details and send reminder invitation for invited vendors until vendor completes their registration. | 2020-06-15 | 2020-06-22
PG | 15 | Property Manager | Vendors | Listing Page | Low | Ready for PROD | Vendors appear in red and green stars. Only show a star if vendor is starred. | 2020-06-15 | 2020-06-18
PG | 15 | Property Manager | Vendors | Listing Page | Medium | Ready for PROD | Advanced search not working | 2020-06-15 | 2020-06-18
PG | 15 | Property Manager | Vendors | Listing Page | Medium | Ready for PROD | Invited vendors should NOT appear on this page. Maybe we should have a checkbox for "Invited Vendors" in advanced search. | 2020-06-15 | 2020-06-18
| 15 | Property Manager | Vendors | Listing Page | High | Complete | All vendors are not shown on this page. There are more vendors in the Administrator portal than those that appear in the manager portal. | 2020-06-18 | 2020-06-22
| 15 | Property Manager | Vendors | Listing Page | Medium | Complete | Search and advanced search not working. Search text should search by vendor name and services offered. | 2020-06-18 | 2020-06-22
| 15 | Property Manager | Vendors | Listing Page | Medium | Complete | Change "STAR" column to say "STATUS". Show status as "Starred" if vendor is a starred vendor. Show status as "Invited" if vendor was sent an invitation but has not yet signed up. | 2020-06-18 | 2020-06-22
| 15 | Property Manager | Vendors | Listing Page | Medium | Not Started | Search text box should search by vendor company name and services. Currently it's only searching by vendor company name.
| 15 | Property Manager | Vendors | Listing Page | Low | Not Started | Advanced search window should close after "Search" button is clicked.
PG |  | Property Manager | Vendors | Vendor List | Medium | Ready for PROD | Cannot star and unstar a vendor | 2020-06-15 | 2020-06-18
PG | 17 | Property Manager | Vendors | View Vendor Details | Medium | Ready for PROD | Can't mark or unmark vendor as a starred vendor | 2020-06-11 | 2020-06-18
RR | 17 | Property Manager | Vendors | View Vendor Details | Low | Complete | Vendor details show empty row for insurance document even when no document was uploaded. | 2020-06-18 | 2020-06-22
RR | 17 | Property Manager | Vendors | View Vendor Details | High | Complete | Manager is able to delete vendor service and documents. Remove delete icon. | 2020-06-18 | 2020-06-22
RR | 17 | Property Manager | Vendors | View Vendor Details | High | Complete | After marking vendor as "Starred" vendor was removed from the vendor list. | 2020-06-18 | 2020-06-22
| 68 | Property Manager | Work Orders | Add Work Order Step 3 | High | Ready for PROD | Even when vendors exist for a particular service category get message saying that no vendors exist. | 2020-07-02 | 2020-07-13
RR | 68 | Property Manager | Work Orders | Add Work Order Step 3 | High | Ready for PROD | Able to submit a work order even when no vendors are added to the work order. "Submit" button should be disabled until at least one vendor is added. | 2020-07-02 | 2020-07-13
RR | 68 | Property Manager | Work Orders | Add Work Order Step 3 | High | Ready for PROD | Able to submit a work order even when no vendors are added to the work order. After submitting the work order go to the list page and back to the added work order - 5 vendors are now added to this work order. | 2020-07-02 | 2020-07-13
| 68 | Property Manager | Work Orders | Add additional vendor to work order | High | Not Started | When a vendor declines the work order invitation or doesn't respond within the time allocated then system should automatically add another vendor to the work order and send out the invitation. This should be done until we get a response from the vendor or no more vendors exist for this service category.
SP |  | property manager | bid requests | New Bid Request | Medium | Complete | Prior to submitting the new bid the status already says "in progress on all vendors and the view bid eyeball button is active. Prior to submit it is impossible for there to be a bid to review and the status should be blank at this point. After submittal then the vendors have an opportunity to create bids. | 2020-06-19 | 2020-06-22
RR |  | property manager | Staff Directory | add staff | High | Complete | when submitting a new staff the system processes for a long time. Please review performance in this area. No response after 2 full min. | 2020-06-19 | 2020-06-22
RR | 95 | Vendor Portal | Bid Requests | View Bid request | High | Ready for PROD | When bid request is "Declined", can't go back to view bid request details. Should allow vendor to "Accept" bid request if there's still time. | 2020-06-22 | 2020-07-15
| 95 | Vendor Portal | Bid Requests | View Bid request | High | Ready for PROD | Vendor should not be allowed to "Accept" or "Decline" bid invitation if time to respond has passed. (same applies to work orders) | 2020-07-02 | 2020-07-13
|  | Vendor Registration |  |  | Medium | Complete | Legal name and Tax ID are not required | 2020-06-22 | 2020-06-22
|  | Vendor Registration |  |  | Medium | Complete | On the primary contact step, email if exists shows correct error message but allows user to go to the services step | 2020-06-22 | 2020-06-22
|  | Vendor Registration |  |  | Low | Ready for PROD | Convert services to three separate dropdowns for ease of use | 2020-06-22 | 2020-07-10
|  | Vendor Registration |  |  | Low | Not Started | File upload doesn't show multiple files uploaded | 2020-06-22 |  | Need to discuss
|  | Vendor Registration |  |  | High | Complete | Credit card verification shows spinning logo and does not go to the next step | 2020-06-22 | 2020-06-22 | Invalid
|  | General |  | Search algorithm | High | In Progress | Need to verify all criterias are implemented as expected | 2020-07-02
|  | General |  | Add additional vendors to bids | High | Not Started | When a vendor declines to submit a bid
|  | Property Manager | Property | Property list | Medium | Deferred | Non-admin property manager should not be able to create a property, edit details or change property managers. Can add documents or change default amounts. | 2020-07-06
|  | Property Manager | Property | Property list | Medium | Not Started | Vendor list for property manager should allow ability to Star/unstar easily (aka one click) on the vendor details page the red delete button the “mark as unstar” seems odd. | 2020-07-06
|  | Property Manager | Create Work Order | Add Vendor | Medium | Deferred | There was no default vendor when creating a work order. | 2020-07-06
|  | Property Manager | Create Work Order | Add Vendor | Medium | Ready for PROD | Add vendor pop up should allow filter by service(s) | 2020-07-06 | 2020-07-13 | Added label of Service which has been selected on Adding Bid/Work Order.
|  | Property Manager | Create Work Order | Work Order Review/Submit | Medium | Not Started | When going to review page. First Bid request review page appeared, then processing, then work order review page appeared. | 2020-07-06
|  | Property Manager | Create Work Order | Add Vendor | Medium | Ready for PROD | On work order review page the add vendor button should not be available. Maybe instead it should be “replace vendor” because there can only be one vendor at a time on a work order. | 2020-07-06 | 2020-07-13
|  | Property Manager | Create Work Order | Work Order Review/Submit | Medium | Not Started | The message feature of a work order should be a tab on the main work order details page. | 2020-07-06
|  | Property Manager | Create Work Order | Work Order Review/Submit | Medium | Not Started | I don't like the confirmation popup. I don't think confirmation is necessary and an extra step with low value. (also the message in the pop up says “didn't work order). | 2020-07-06
|  | Property Manager | Work Order | Work Order List | Medium | Not Started | After submitting the work order, There was a red action bell in the work order list. I am not sure what action was needed | 2020-07-06
|  | Property Manager | Work Order | Work Order Detail | Medium | Not Started | When clicking on the red action bell to get to the work order detail page there are not two vendors (I had tried to add a second vendor prior to submitting as a test, but there was only one on the screen when I submitted. It must have put in DB a 2nd and not displayed). There can only be one vendor on a work order. | 2020-07-06

## Top 5 Action Items
Action Item | Criteria | Display Text (2 columns - text, date) | Action
Credit Card about to expire | 30 days before expiration | Credit card (xxxx) expiring soon (show date in 2nd column) | Go to credit card update page
Insurance about to expire | 30 days before expiration | Insurance expiring soon (show date in 2nd column) | Go to insurance update page
Respond to bid request | Until date > bid respond by date | Bid Title - Respond by (show date in 2nd column) | Go to specific bid request
Submit bid | Until date > bid submit date | Bid Title - Submit by (show date in 2nd column) | Go to specific work order
Respond to work order | Until date > work order respond by date | Work Order Title - Respond by (show date in 2nd column) | Go to specific bid request
Submit bid | Until date > work order submit date | Work Order Title - Submit by (show date in 2nd column) | Go to specific work order

## Status
Not Started | Low
In Progress | Medium
Ready for QA | High
Ready for PROD | Enhancement 1
Complete | Enhancement 2
Deferred
Already working
Failed QA
Failed PROD